## Issue Report
Title | Description | Issue ID | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
Sign up | The Sign Up use case describes the process by which new users create an account on a social networking platform. This use case enables individuals to provide their personal information, such as their name, email address, and password, in order to register and gain access to the platform's features and functionalities. | 1 | Closed | Nguyen Anh Viet | 2023-05-15 | 2023-06-04 | iter1 | WP, 3_Done | Sign up
Write SRS for Sign up | Write detailed functional specification for the Sign up | 2 | Closed | Nguyen Anh Viet | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | Sign up
Write SDS for Sign up | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Sign up | 3 | Closed | Nguyen Anh Viet | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | Sign up
Write Code for Sign up | Code & Unit test for the Sign up | 4 | Closed | Nguyen Anh Viet | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | Sign up
Integrate User Login screen with others | Integrate the User Login screen with other screens | 5 | Closed | Nguyen Anh Viet | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | Sign up
No User Register link on Home Page screen | The link User Register is missed on the Mockup of the Home Page screen (SRS document) | 6 | Closed | Nguyen Anh Viet | 2023-05-15 | 2023-06-04 | none | Defect, 3_Done | Home Page
Login | The Login Use use case describes the process of a social networking platform allows users to access their personal accounts using their registered username and password. Users enter their login credentials and then click the "Submit" button to log in to the system. Additionally, this feature provides a "Remember Me" option to save the login | 7 | Closed | Nguyen Anh Viet | 2023-05-15 | 2023-06-04 | iter1 | WP, 3_Done | Login
Write SRS for Login | Write detailed functional specification for the Login | 8 | Closed | Nguyen Anh Viet | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | Login
Write SDS for Login | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Login | 9 | Closed | Nguyen Anh Viet | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | Login
Write Code for Login | Code & Unit test for the Login | 10 | Closed | Nguyen Anh Viet | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | Login
Forgot Password | The Forgot Password feature allows users to recover their forgotten passwords by entering their registered email address and verification code received via email. This feature consists of an email field, an email code field, and a submit button. Users enter their email, receive the code, enter it, and submit to verify and reset their password. | 11 | Closed | Nguyen Anh Viet | 2023-05-15 | 2023-06-04 | iter1 | WP, 3_Done | Forgot Password
Write SRS for Forgot Password | Write detailed functional specification for the Forgot Password | 12 | Closed | Nguyen Anh Viet | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | Forgot Password
Write SDS for Forgot Password | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Forgot Password | 13 | Closed | Nguyen Anh Viet | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | Forgot Password
Write Code for Forgot Password | Code & Unit test for the Forgot Password | 14 | Closed | Nguyen Anh Viet | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | Forgot Password
Logout | The logout function in a social networking platform allows users to log out of their accounts. When a user selects the logout function, the system will confirm and terminate the user's current login session, redirecting them to either the login page or the main page of the social networking platform. The logout function ensures the security and privacy of users by allowing them to exit their accounts and prevent unauthorised access to their personal information. | 15 | Closed | Nguyen Anh Viet | 2023-05-15 | 2023-06-04 | iter1 | WP, 3_Done | Logout
Write SRS for Logout | Write detailed functional specification for the Logout | 16 | Closed | Nguyen Anh Viet | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | Logout
Write SDS for Logout | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Logout | 17 | Closed | Nguyen Anh Viet | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | Logout
Write Code forLogout | Code & Unit test for the Logout | 18 | Closed | Nguyen Anh Viet | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | Logout
Edit Profile | The function of changing user personal information on a platform allows users to modify their account details. It provides users with control over their personal information, enabling them to update and protect their accounts while enhancing security and privacy. | 19 | Closed | Nguyen Ho Ngoc An | 2023-05-15 | 2023-06-04 | iter1 | WP, 3_Done | Edit Profile
Write SRS for Edit Profile | Write detailed functional specification for the Edit Profile | 20 | Closed | Nguyen Ho Ngoc An | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | Edit Profile
Write SDS for Edit Profile | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Edit Profile | 21 | Closed | Nguyen Ho Ngoc An | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | Edit Profile
Write Code for Edit Profile | Code & Unit test for the Edit Profile | 22 | Closed | Nguyen Ho Ngoc An | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | Edit Profile
Find User | The function of finding a user allows users to search for specific individuals by entering their name. Users can browse through the search results to access the desired person's profile and initiate connections or interactions. This function facilitates social connections and expands one's network within the platform. | 23 | Closed | Nguyen Ho Ngoc An | 2023-06-05 | 2023-06-25 | iter2 | WP, 3_Done | Find User
Write SRS for Find User | Write detailed functional specification for the Find User | 24 | Closed | Nguyen Ho Ngoc An | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | Find User
Write SDS for Find User | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Find User | 25 | Closed | Nguyen Ho Ngoc An | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | Find User
Write Code for Find User | Code & Unit test for the Find User | 26 | Closed | Nguyen Ho Ngoc An | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | Find User
View Profile | Viewing a personal profile allows users to access and manage their account information, privacy settings, and online identity. It offers control over personal details, enhances security, and enables customization of privacy preferences. | 27 | Closed | Nguyen Ho Ngoc An | 2023-05-15 | 2023-06-04 | iter1 | WP, 3_Done | View Profile
Write SRS for View Profile | Write detailed functional specification for the View Profile | 28 | Closed | Nguyen Ho Ngoc An | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | View Profile
Write SDS for View Profile | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the View Profile | 29 | Closed | Nguyen Ho Ngoc An | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | View Profile
Write Code for View Profile | Code & Unit test for the View Profile | 30 | Closed | Nguyen Ho Ngoc An | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | View Profile
View Post | The function of viewing posts allows users to explore and interact with a variety of content shared by friends. Users can access their News Feed or specific profiles to see a stream of posts, including text, photos, videos, and links. They can engage with posts by liking, commenting, or sharing, fostering connections and conversations within the community. This function offers users a personalised and dynamic way to stay connected and informed. | 31 | Closed | Nguyen Ho Ngoc An | 2023-05-15 | 2023-06-04 | iter1 | WP, 3_Done | View Post
Write SRS for View Post | Write detailed functional specification for the View Post | 32 | Closed | Nguyen Ho Ngoc An | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | View Post
Write SDS for View Post | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the View Post | 33 | Closed | Nguyen Ho Ngoc An | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | View Post
Write Code for View Post |  | 34 | Closed | Nguyen Ho Ngoc An | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | View Post
Create Post | The posting function in a social networking platform allows users to create and share content with others. When a user selects the posting function, they can create a new post by composing content and attaching images or videos. After the user completes the post, they can choose to publish it, making it visible to their friends or the wider network, depending on their privacy settings. The posting function facilitates communication, sharing of thoughts, and engagement with other users on the social networking platform. | 35 | Closed | Nguyen Duy Khanh | 2023-05-15 | 2023-06-04 | iter1 | WP, 3_Done | Create Post
Write SRS for Create Post | Write detailed functional specification for the Create Post | 36 | Closed | Nguyen Duy Khanh | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | Create Post
Write SDS for Create Post | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Create Post | 37 | Closed | Nguyen Duy Khanh | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | Create Post
Write Code for Create Post | Code & Unit test for the Create Post | 38 | Closed | Nguyen Duy Khanh | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | Create Post
Update Post | The editing feature on social networking platforms allows users to modify and refine their existing posts, ensuring accuracy and relevance. This functionality empowers users to maintain up-to-date information and improve the quality of their shared content. | 39 | Closed | Nguyen Duy Khanh | 2023-05-15 | 2023-06-04 | iter1 | WP, 3_Done | Update Post
Write SRS for Update Post | Write detailed functional specification for the Update Post | 40 | Closed | Nguyen Duy Khanh | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | Update Post
Write SDS for Update Post | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Update Post | 41 | Closed | Nguyen Duy Khanh | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | Update Post
Write Code for Update Post | Code & Unit test for the Update Post | 42 | Closed | Nguyen Duy Khanh | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | Update Post
Delete Post | The ability to delete posts on social networking platforms provides users with the option to remove their previously published content. This feature ensures control over shared information and allows users to manage their online presence effectively. | 43 | Closed | Nguyen Duy Khanh | 2023-05-15 | 2023-06-04 | iter1 | WP, 3_Done | Delete Post
Write SRS for Delete Post | Write detailed functional specification for the Delete Post | 44 | Closed | Nguyen Duy Khanh | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | Delete Post
Write SDS for Delete Post | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Delete Post | 45 | Closed | Nguyen Duy Khanh | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | Delete Post
Write Code for Delete Post | Code & Unit test for the Delete Post | 46 | Closed | Nguyen Duy Khanh | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | Delete Post
Share Post | The sharing function on social networking platforms enables users to distribute and disseminate interesting content with their network. By sharing posts, users can contribute to discussions, spread awareness, and engage with others. | 47 | Closed | Nguyen Duy Khanh | 2023-05-15 | 2023-06-04 | iter1 | WP, 3_Done | Share Post
Write SRS for Share Post | Write detailed functional specification for the Share Post | 48 | Closed | Nguyen Duy Khanh | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | Share Post
Write SDS for Share Post | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Share Post | 49 | Closed | Nguyen Duy Khanh | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | Share Post
Write Code for Share Post | Code & Unit test for the Share Post | 50 | Closed | Nguyen Duy Khanh | 2023-05-15 | 2023-06-04 | iter1 | Task, 3_Done | Share Post
View Comment | The comment feature on social networking platforms allows users to engage in conversations, provide feedback, and share their thoughts on shared posts. By viewing comments, users can actively participate in discussions, gain insights, and build connections within their network. | 51 | Closed | Nguyen Duy Khanh | 2023-06-05 | 2023-06-25 | iter2 | WP, 3_Done | View Comment
Write SRS for View Comment | Write detailed functional specification for the View Commnet | 52 | Closed | Nguyen Duy Khanh | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | View Comment
Write SDS for View Comment | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the View Comment | 53 | Closed | Nguyen Duy Khanh | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | View Comment
Write Code for View Comment | Code & Unit test for the View Comment | 54 | Closed | Nguyen Duy Khanh | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | View Comment
Create Comment | The commenting function on social networking platforms allows users to engage in conversations, share their thoughts, and provide feedback on shared content. By leveraging the commenting feature, users can actively participate in discussions, express their opinions, and foster connections within the online community. | 55 | Closed | Nguyen Duy Khanh | 2023-06-05 | 2023-06-25 | iter2 | WP, 3_Done | Create Comment
Write SRS for Create Comment | Write detailed functional specification for the Create Comment | 56 | Closed | Nguyen Duy Khanh | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | Create Comment
Write SDS for Create Comment | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Create Comment | 57 | Closed | Nguyen Duy Khanh | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | Create Comment
Write Code for Create Comment | Code & Unit test for the Create Comment | 58 | Closed | Nguyen Duy Khanh | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | Create Comment
Update Comment | The editing feature on social networking platforms allows users to modify and refine their existing comments, ensuring accuracy and relevance. This functionality empowers users to update their thoughts, provide additional context, or make necessary revisions to their shared comments. By enabling comment modification, users can actively participate in discussions, contribute valuable insights, and enhance the overall quality of conversations. | 59 | Closed | Nguyen Duy Khanh | 2023-06-05 | 2023-06-25 | iter2 | WP, 3_Done | Update Comment
Write SRS for Update Comment | Write detailed functional specification for the Update Comment | 60 | Closed | Nguyen Duy Khanh | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | Update Comment
Write SDS for Update Comment | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Update Comment | 61 | Closed | Nguyen Duy Khanh | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | Update Comment
Write Code for Update Comment | Code & Unit test for the Update Comment | 62 | Closed | Nguyen Duy Khanh | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | Update Comment
Delete Comment | The ability to delete comments on social networking platforms provides users with the option to remove their previously posted content. This feature ensures control over shared information and allows users to manage their online presence effectively. By being able to delete comments, users can maintain the accuracy and relevance of their expressed opinions, as well as ensure the privacy of their personal information. | 63 | Closed | Nguyen Duy Khanh | 2023-06-05 | 2023-06-25 | iter2 | WP, 3_Done | Delete Comment
Write SRS for Delete Comment | Write detailed functional specification for the Delete Comment | 64 | Closed | Nguyen Duy Khanh | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | Delete Comment
Write SDS for Delete Comment | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Delete Comment | 65 | Closed | Nguyen Duy Khanh | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | Delete Comment
Write Code for Delete Comment | Code & Unit test for the Delete Comment | 66 | Closed | Nguyen Duy Khanh | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | Delete Comment
Add Friend | Connecting with others on social media is a common and important activity for building relationships and expanding one's online social network. When friending people on social media, users can search, connect, and communicate with others who share similar interests, concerns, or common goals. | 67 | Closed | Nguyen Anh Viet | 2023-06-05 | 2023-06-25 | iter2 | WP, 3_Done | Add Friend
Write SRS for Add Friend | Write detailed functional specification for the Add Friend | 68 | Closed | Nguyen Anh Viet | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | Add Friend
Write SDS for Add Friend | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Add Friend | 69 | Closed | Nguyen Anh Viet | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | Add Friend
Write Code for Add Friend | Code & Unit test for the Add Friend | 70 | Closed | Nguyen Anh Viet | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | Add Friend
Accept Friend Request | The "Accept Friend Request" function in a social network allows users to confirm and accept friend requests from others. This is an important part of building an online social network and expanding personal relationships. | 71 | Closed | Nguyen Anh Viet | 2023-06-05 | 2023-06-25 | iter2 | WP, 3_Done | Accept Friend Request
Write SRS for Accept Friend Request | Write detailed functional specification for the Accept Friend Request | 72 | Closed | Nguyen Anh Viet | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | Accept Friend Request
Write SDS for Accept Friend Request | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Accept Friend Request | 73 | Closed | Nguyen Anh Viet | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | Accept Friend Request
Write Code for Accept Friend Request | Code & Unit test for the Accept Friend Request | 74 | Closed | Nguyen Anh Viet | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | Accept Friend Request
Unfriend | "Unfriend a friend" is a function in a social networking system that allows a user to unconnect with a friend in his or her friends list. This functionality provides users with the ability to manage and regulate friendships on the platform. | 75 | Closed | Nguyen Duy Khanh | 2023-06-05 | 2023-06-25 | iter2 | WP, 3_Done | Unfriend
Write SRS for Unfriend | Write detailed functional specification for the Unfriend | 76 | Closed | Nguyen Duy Khanh | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | Unfriend
Write SDS for Unfriend | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Unfriend | 77 | Closed | Nguyen Duy Khanh | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | Unfriend
Write Code for Unfriend | Code & Unit test for the Unfriend | 78 | Closed | Nguyen Duy Khanh | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | Unfriend
View Friend List | "View Friends List" is a feature in the system that allows users to view a list of their connected friends on the platform. This feature provides a user-friendly interface for users to access and manage their friends' list. | 79 | Closed | Nguyen Duy Khanh | 2023-06-05 | 2023-06-25 | iter2 | WP, 3_Done | View Friend List
Write SRS for View Friend List | Write detailed functional specification for the View Friend List | 80 | Closed | Nguyen Duy Khanh | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | View Friend List
Write SDS for View Friend List | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Friend List | 81 | Closed | Nguyen Duy Khanh | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | View Friend List
Write Code for View Friend List | Code & Unit test for the View Friend List | 82 | Closed | Nguyen Duy Khanh | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | View Friend List
Send Message | The Send Message use case describes the process by which a user sends a message to another user within the system. This use case enables users to initiate private conversations, engage in direct communication, and share information with others. | 83 | Closed | Nguyen Hong Linh | 2023-06-05 | 2023-06-25 | iter2 | WP, 3_Done | Send Message
Write SRS for Send Message | Write detailed functional specification for the Send Message | 84 | Closed | Nguyen Hong Linh | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | Send Message
Write SDS for Send Message | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Message | 85 | Closed | Nguyen Hong Linh | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | Send Message
Write Code for Send Message | Code & Unit test for the Send Message | 86 | Closed | Nguyen Hong Linh | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | Send Message
View Message | The View Message use case describes the process by which a user views a received message within the system. This use case enables users to access their message chatBox to read and interact with messages they have received. | 87 | Closed | Nguyen Hong Linh | 2023-06-05 | 2023-06-25 | iter2 | WP, 3_Done | View Message
Write SRS for View Message | Write detailed functional specification for the View Message | 88 | Closed | Nguyen Hong Linh | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | View Message
Write SDS for View Message | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the View Message | 89 | Closed | Nguyen Hong Linh | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | View Message
Write Code for View Message | Code & Unit test for the View Message | 90 | Closed | Nguyen Hong Linh | 2023-06-05 | 2023-06-25 | iter2 | Task, 3_Done | View Message
Create Brand | The brand-building function in social media is a feature that helps users build and manage their brand on the social media platform. It provides users with tools and resources to create and shape brand elements such as logo, intro, email, phone, address. The brand-building function also offers tools for users to create advertisements based on their brand. | 91 | Closed | Nguyen Anh Viet | 2023-06-26 | 2023-07-16 | iter3 | WP, 3_Done | Create Brand
Write SRS for Create Brand | Write detailed functional specification for the Create Brand | 92 | Closed | Nguyen Anh Viet | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Create Brand
Write SDS for Create Brand | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Create Brand | 93 | Closed | Nguyen Anh Viet | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Create Brand
Write Code for Create Brand | Code & Unit test for the Create Brand | 94 | Closed | Nguyen Anh Viet | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Create Brand
Report User | The Report User use case describes the process by which a user reports another user for inappropriate behavior, harassment, or violation of community guidelines. This use case enables users to flag problematic users, allowing administrators to review and take appropriate action. | 95 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | WP, 3_Done | Report User
Write SRS for Report User | Write detailed functional specification for the Report User | 96 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Report User
Write SDS for Report User | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Report User | 97 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Report User
Write Code for Report User | Code & Unit test for the Report User | 98 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Report User
Report Post | The Report Post use case describes the process by which a user reports a post that violates the platform's guidelines or contains inappropriate content. This use case enables users to flag posts that they find offensive, harmful, or in violation of community standards, allowing administrators to review and take appropriate action. | 99 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | WP, 3_Done | Report Post
Write SRS for Report Post | Write detailed functional specification for the Report Post | 100 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Report Post
Write SDS for Report Post | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Report Post | 101 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Report Post
Write Code for Report Post |  | 102 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Report Post
Report Comment | The Report Comment use case describes the process by which a user reports a comment that violates the platform's guidelines or contains inappropriate content. This use case enables users to flag comments that they find offensive, harmful, or in violation of community standards, allowing administrators to review and take appropriate action. | 103 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | WP, 3_Done | Report Comment
Write SRS for Report Comment | Write detailed functional specification for the Report Comment | 104 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Report Comment
Write SDS for Report Comment | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Report Comment | 105 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Report Comment
Write Code for Report Comment | Code & Unit test for the Report Comment | 106 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Report Comment
View Post Report | The View Post Report use case describes the process by which an administrator views a list post report within the system. | 107 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | WP, 3_Done | View Post Report
Write SRS for View Post Report | Write detailed functional specification for the View Post Report | 108 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | View Post Report
Write SDS for View Post Report | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the View Post Report | 109 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | View Post Report
Write Code for View Post Report | Code & Unit test for the View Post Report | 110 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | View Post Report
Delete Post Report | The Delete Port Report use case describes the process by which an administrator deletes a port report from the system. This use case enables administrators to permanently remove port reports for various reasons, such as outdated information, duplicate entries, or data privacy considerations. | 111 | Closed | Nguyen Duy Khanh, Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | WP, 3_Done | Delete Post Report
Write SRS for Delete Post Report | Write detailed functional specification for the Delete Post Report | 112 | Closed | Nguyen Duy Khanh, Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Delete Post Report
Write SDS for Delete Post Report | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Delete Post Report | 113 | Closed | Nguyen Duy Khanh, Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Delete Post Report
Write Code for Delete Post Report | Code & Unit test for the Delete Post Report | 114 | Closed | Nguyen Duy Khanh, Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Delete Post Report
View Comment Report | The View Comment Report use case describes the process by which an administrator views a list comment report within the system. | 115 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | WP, 3_Done | View Comment Report
Write SRS for View Comment Report | Write detailed functional specification for the View Comment Report | 116 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | View Comment Report
Write SDS for View Comment Report | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the View Comment Report | 117 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | View Comment Report
Write Code for View Comment Report | Code & Unit test for the View Comment Report | 118 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | View Comment Report
Delete Comment Report | The Delete Comment Report use case describes the process by which an administrator deletes a comment report from the system. This use case enables administrators to permanently remove comment reports for various reasons, such as inappropriate content, spam, or policy violations. The deletion of comment reports helps maintain the integrity and quality of user-generated content within the system. | 119 | Closed | Nguyen Duy Khanh, Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | WP, 3_Done | Delete Comment Report
Write SRS for Delete Comment Report | Write detailed functional specification for the Delete Comment Report | 120 | Closed | Nguyen Duy Khanh, Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Delete Comment Report
Write SDS for Delete Comment Report | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Delete Comment Report | 121 | Closed | Nguyen Duy Khanh, Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Delete Comment Report
Write Code for Delete Comment Report | Code & Unit test for the Delete Comment Report | 122 | Closed | Nguyen Duy Khanh, Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Delete Comment Report
View User Report | The View User Report use case describes the process by which an administrator views a list user's account report within the system. | 123 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | WP, 3_Done | View User Report
Write SRS for View User Report | Write detailed functional specification for the View User Report | 124 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | View User Report
Write SDS for View User Report | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the View User Report | 125 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | View User Report
Write Code for View User Report | Code & Unit test for the View User Report | 126 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | View User Report
Lock User Account | The Lock User Account use case describes the process by which an administrator locks a user's account within the system. This use case enables administrators to restrict user access and prevent further use of the account due to violations, suspicious activities, or other administrative reasons. | 127 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | WP, 3_Done | Lock User Account
Write SRS for Lock User Account | Write detailed functional specification for the Lock User Account | 128 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Lock User Account
Write SDS for Lock User Account | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Lock User Account | 129 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Lock User Account
Write Code for Lock User Account | Code & Unit test for the Look User Account | 130 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Lock User Account
Delete User Account | The Delete User Account use case describes the process by which an administrator deletes a user's account from the system. This use case enables administrators to permanently remove user accounts due to various reasons, such as policy violations or user request. | 131 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | WP, 3_Done | Delete User Account
Write SRS for Delete User Account | Write detailed functional specification for the Delete User Account | 132 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Delete User Account
Write SDS for Delete User Account | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Delete User Account | 133 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Delete User Account
Write Code for Delete User Account | Code & Unit test for the Delete User Account | 134 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Delete User Account
View Statistics | The View Statistics use case describes the process by which an administrator or master admin views statistical information and data related to the system's usage and performance. This use case enables administrators to gather insights, track key metrics, and analyze trends to make informed decisions and improve the system. | 135 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | WP, 3_Done | View Statistics
Write SRS for View Statistics | Write detailed functional specification for the View Statistics | 136 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | View Statistics
Write SDS for View Statistics | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the View Statistics | 137 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | View Statistics
Write Code for View Statistics | Code & Unit test for the View Statistics | 138 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | View Statistics
Grant Admin Rights | The Grant Admin Rights use case describes the process by which the Master Admin grants administrator rights to a user in the system. This use case enables the Master Admin to delegate administrative privileges to trusted users who can assist in managing the system. | 139 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | WP, 3_Done | Grant Admin Rights
Write SRS for Grant Admin Rights | Write detailed functional specification for the Grand Admin Rights | 140 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Grant Admin Rights
Write SDS for Grant Admin Rights | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Grant Admin Rights | 141 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Grant Admin Rights
Write Code for Grant Admin Rights | Code & Unit test for the Grant Admin Rights | 142 | Closed | Nguyen Hong Linh | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Grant Admin Rights
Add ADS | The "Add Ads" function in social networks is a feature that allows users to create and post advertisements on social networking platforms. | 143 | Closed | Nguyen Ho Ngoc An | 2023-06-26 | 2023-07-16 | iter3 | WP, 3_Done | Add ADS
Write SRS for Add ADS | Write detailed functional specification for the Add ADS | 144 | Closed | Nguyen Ho Ngoc An | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Add ADS
Write SDS for Add ADS | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Add ADS | 145 | Closed | Nguyen Ho Ngoc An | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Add ADS
Write Code for Add ADS | Code & Unit test for the Add ADS | 146 | Closed | Nguyen Ho Ngoc An | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Add ADS
View ADS | The "View Ads Inventory" function allows users to access and browse the available ads inventory. It provides users with a comprehensive overview of the advertisements that are currently active and available for display. | 147 | Closed | Nguyen Ho Ngoc An | 2023-06-26 | 2023-07-16 | iter3 | WP, 3_Done | View ADS
Write SRS for View ADS | Write detailed functional specification for the View ADS | 148 | Closed | Nguyen Ho Ngoc An | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | View ADS
Write SDS for View ADS | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the View ADS | 149 | Closed | Nguyen Ho Ngoc An | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | View ADS
Write Code for View ADS | Code & Unit test for the View ADS | 150 | Closed | Nguyen Ho Ngoc An | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | View ADS
Update ADS | The "Update Ads" function is a crucial feature in a social network platform that allows advertisers to modify and manage their existing advertisements. This function provides advertisers with the flexibility to make adjustments, improvements, or updates to their ads to ensure they remain relevant and effective in reaching their target audience | 151 | Closed | Nguyen Ho Ngoc An | 2023-06-26 | 2023-07-16 | iter3 | WP, 3_Done | Update ADS
Write SRS for Update ADS | Write detailed functional specification for the Update ADS | 152 | Closed | Nguyen Ho Ngoc An | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Update ADS
Write SDS for Update ADS | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Update ADS | 153 | Closed | Nguyen Ho Ngoc An | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Update ADS
Write Code for Update ADS | Code & Unit test for the Update ADS | 154 | Closed | Nguyen Ho Ngoc An | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Update ADS
Delete ADS | The "Delete Ads" function in a social network allows users to remove specific ads from their advertising campaigns. This function provides a convenient way for advertisers to manage their ad content and make adjustments as needed. | 155 | Closed | Nguyen Ho Ngoc An | 2023-06-26 | 2023-07-16 | iter3 | WP, 3_Done | Delete ADS
Write SRS for Delete ADS | Write detailed functional specification for the Delete ADS | 156 | Closed | Nguyen Ho Ngoc An | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Delete ADS
Write SDS for Delete ADS | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Delete ADS | 157 | Closed | Nguyen Ho Ngoc An | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Delete ADS
Write Code for Delete ADS | Code & Unit test for the Delete ADS | 158 | Closed | Nguyen Ho Ngoc An | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Delete ADS
Pay for ADS | The "Pay for ADS" function is a paid advertising feature provided by the social network that allows users to promote their content, products, or services to a larger audience by investing money. With this function, users can ensure that their ads are displayed within the news feed of the social network, increasing their visibility and reaching a wider user base. | 159 | Closed | Nguyen Ho Ngoc An | 2023-06-26 | 2023-07-16 | iter3 | WP, 3_Done | Pay for ADS
Write SRS for Pay for ADS | Write detailed functional specification for the Pay for ADS | 160 | Closed | Nguyen Ho Ngoc An | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Pay for ADS
Write SDS for Pay for ADS | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Pay for ADS | 161 | Closed | Nguyen Ho Ngoc An | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Pay for ADS
Write Code for Pay for ADS | Code & Unit test for the Pay for ADS | 162 | Closed | Nguyen Ho Ngoc An | 2023-06-26 | 2023-07-16 | iter3 | Task, 3_Done | Pay for ADS