## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Function - Sign up | Sign Up | Guest | The Sign Up use case describes the process by which new users create an account on a social networking platform. This use case enables individuals to provide their personal information, such as their name, email address, and password, in order to register and gain access to the platform's features and functionalities. | Nguyen Anh Viet | Done | iter1 | none
2 | Function - Login | Login | User, Admin, Master Admin | The Login Use use case describes the process of a social networking platform allows users to access their personal accounts using their registered username and password. Users enter their login credentials and then click the "Submit" button to log in to the system. Additionally, this feature provides a "Remember Me" option to save the login information for future access, making it more convenient and time-saving for users to log back into their accounts. | Nguyen Anh Viet | Done | iter1 | none
3 | Function - Forgot Password | Forgot Password | User, Admin, Master Admin | The Forgot Password feature allows users to recover their forgotten passwords by entering their registered email address and verification code received via email. This feature consists of an email field, an email code field, and a submit button. Users enter their email, receive the code, enter it, and submit to verify and reset their password | Nguyen Anh Viet | Done | iter1 | none
4 | Function - Logout | Logout | User, Admin, Master Admin | The logout function in a social networking platform allows users to log out of their accounts. When a user selects the logout function, the system will confirm and terminate the user's current login session, redirecting them to either the login page or the main page of the social networking platform. The logout function ensures the security and privacy of users by allowing them to exit their accounts and prevent unauthorised access to their personal information. | Nguyen Anh Viet | Done | iter1 | none
5 | Function - Edit Profile | Edit Profile | User, Admin, Master Admin | The function of changing user personal information on a platform allows users to modify their account details. It provides users with control over their personal information, enabling them to update and protect their accounts while enhancing security and privacy. | Nguyen Ho Ngoc An | Done | iter1 | none
6 | Function - Find User | Find a user in social network | User, Admin, Master Admin | The function of finding a user allows users to search for specific individuals by entering their name. Users can browse through the search results to access the desired person's profile and initiate connections or interactions. This function facilitates social connections and expands one's network within the platform. | Nguyen Ho Ngoc An | Done | iter2 | none
7 | Function - View Profile | View a user's profile page. | User, Admin, Master Admin | Viewing a personal profile allows users to access and manage their account information, privacy settings, and online identity. It offers control over personal details, enhances security, and enables customization of privacy preferences. | Nguyen Ho Ngoc An | Done | iter1 | none
8 | Function - View Post | View posts. | User, Admin, Master Admin | The view posts function enables users to browse and engage with a range of shared content. They can like, comment, and share posts to interact and connect with others. It provides a personalized and dynamic experience for staying connected. | Nguyen Ho Ngoc An | Done | iter1 | none
9 | Function - Create Post | Create an article | User | The posting function enables users to create and share content on a social networking platform. Users can compose text, attach media, and choose their audience before publishing the post. It fosters communication, facilitates sharing of thoughts, and encourages engagement with other platform users. | Nguyen Duy Khanh | Done | iter1 | none
10 | Function - Update Post | Edit a post | User | The editing feature on social networking platforms allows users to modify and refine their existing posts, ensuring accuracy and relevance. This functionality empowers users to maintain up-to-date information and improve the quality of their shared content. | Nguyen Duy Khanh | Done | iter1 | none
11 | Function - Delete Post | Delete a post | User | The ability to delete posts on social networking platforms provides users with the option to remove their previously published content. This feature ensures control over shared information and allows users to manage their online presence effectively. | Nguyen Duy Khanh | Done | iter1 | none
12 | Function - Share Post | Share a post | User | The sharing function on social networking platforms enables users to distribute and disseminate interesting content with their network. By sharing posts, users can contribute to discussions, spread awareness, and engage with others. | Nguyen Duy Khanh | Done | iter1 | none
13 | Function - View Comment | View a comment | User | The comment feature on social networking platforms allows users to engage in conversations, provide feedback, and share their thoughts on shared posts. By viewing comments, users can actively participate in discussions, gain insights, and build connections within their network. | Nguyen Duy Khanh | Done | iter2 | none
14 | Function - Create Comment | Create a comment | User | The commenting function on social networking platforms allows users to engage in conversations, share their thoughts, and provide feedback on shared content. By leveraging the commenting feature, users can actively participate in discussions, express their opinions, and foster connections within the online community. | Nguyen Duy Khanh | Done | iter2 | none
15 | Function - Update Comment | Edit a Comment | User | The editing feature on social networking platforms enables users to modify and improve their comments. It allows users to update their thoughts, provide additional context, and make necessary revisions to their shared comments. This functionality promotes active participation, valuable contributions, and enhanced conversation quality within the platform. | Nguyen Duy Khanh | Done | iter2 | none
16 | Function - Delete Comment | Delete a Comment | User | The delete comment feature on social networking platforms gives users the power to remove their own posted content. This feature allows users to maintain control over the information they share and effectively manage their online presence. By being able to delete comments, users can ensure the accuracy and relevance of their expressed opinions and protect their privacy by removing personal information if needed. | Nguyen Duy Khanh | Done | iter2 | none
17 | Function - Add Friend | Add Friend | User | Connecting with others on social media is a common and important activity for building relationships and expanding one's online social network. When friending people on social media, users can search, connect, and communicate with others who share similar interests, concerns, or common goals. | Nguyen Anh Viet | Done | iter2 | none
18 | Function - Accept Friend Request | Accept Friend Request | User | The "Accept Friend Request" function in a social network allows users to confirm and accept friend requests from others. This is an important part of building an online social network and expanding personal relationships. | Nguyen Anh Viet | Done | iter2 | none
19 | Function - Unfriend | Unfriend | User | "Unfriend a friend" is a function in a social networking system that allows a user to unconnect with a friend in his or her friends list. This functionality provides users with the ability to manage and regulate friendships on the platform. | Nguyen Duy Khanh | Done | iter2 | none
20 | Function - View Friend List | View Friend List | User | "View Friends List" is a feature in the system that allows users to view a list of their connected friends on the platform. This feature provides a user-friendly interface for users to access and manage their friends' list. | Nguyen Duy Khanh | Done | iter2 | none
21 | Function - Send Message | Send Message | User | The Send Message use case describes the process by which a user sends a message to another user within the system. This use case enables users to initiate private conversations, engage in direct communication, and share information with others. | Nguyen Hong Linh | Done | iter2 | none
22 | Function - View Message | View Message | User | The View Message use case describes the process by which a user views a received message within the system. This use case enables users to access their message chatBox to read and interact with messages they have received. | Nguyen Hong Linh | Done | iter2 | none
23 | Function - Create Brand | Create Brand | User | The brand-building function in social media is a feature that helps users build and manage their brand on the social media platform. It provides users with tools and resources to create and shape brand elements such as logo, intro, email, phone, address. The brand-building function also offers tools for users to create advertisements based on their brand. | Nguyen Anh Viet | Done | iter3 | none
24 | Function - Report User | Report a User | User | The Report User use case describes the process by which a user reports another user for inappropriate behavior, harassment, or violation of community guidelines. This use case enables users to flag problematic users, allowing administrators to review and take appropriate action. | Nguyen Hong Linh | Done | iter3 | none
25 | Function - Report Post | Report a Post | User | The Report Post use case describes the process by which a user reports a post that violates the platform's guidelines or contains inappropriate content. This use case enables users to flag posts that they find offensive, harmful, or in violation of community standards, allowing administrators to review and take appropriate action. | Nguyen Hong Linh | Done | iter3 | none
26 | Function - Report Comment | Report a Comment | User | The Report Comment use case describes the process by which a user reports a comment that violates the platform's guidelines or contains inappropriate content. This use case enables users to flag comments that they find offensive, harmful, or in violation of community standards, allowing administrators to review and take appropriate action. | Nguyen Hong Linh | Done | iter3 | none
27 | Function - View Post Report | View Post Report | Admin, Master Admin | The View Post Report use case describes the process by which an administrator views a list post report within the system. | Nguyen Hong Linh | Done | iter3 | none
28 | Function - Delete Post Report | Delete Post Report | Admin, Master Admin | The Delete Port Report use case describes the process by which an administrator deletes a port report from the system. This use case enables administrators to permanently remove port reports for various reasons, such as outdated information, duplicate entries, or data privacy considerations. | Nguyen Duy Khanh, Nguyen Hong Linh | Done | iter3 | none
29 | Function - View Comment Report | View Comment Report | Admin, Master Admin | The View Comment Report use case describes the process by which an administrator views a list comment report within the system. | Nguyen Hong Linh | Done | iter3 | none
30 | Function - Delete Comment Report | Delete Comment Report | Admin, Master Admin | The Delete Comment Report use case describes the process by which an administrator deletes a comment report from the system. This use case enables administrators to permanently remove comment reports for various reasons, such as inappropriate content, spam, or policy violations. The deletion of comment reports helps maintain the integrity and quality of user-generated content within the system. | Nguyen Duy Khanh, Nguyen Hong Linh | Done | iter3 | none
31 | Function - View User Report | View User Report | Admin, Master Admin | The View User Report use case describes the process by which an administrator views a list user's account report within the system. | Nguyen Hong Linh | Done | iter3 | none
32 | Function - Lock User Account | Lock User Account | Admin, Master Admin | The Lock User Account use case describes the process by which an administrator locks a user's account within the system. This use case enables administrators to restrict user access and prevent further use of the account due to violations, suspicious activities, or other administrative reasons. | Nguyen Hong Linh | Done | iter3 | none
33 | Function - Delete User Account | Delete User Account | Admin, Master Admin | The Delete User Account use case describes the process by which an administrator deletes a user's account from the system. This use case enables administrators to permanently remove user accounts due to various reasons, such as policy violations or user request. | Nguyen Hong Linh | Done | iter3 | none
34 | Function - View Statistics | View Statistics | Master Admin | The View Statistics use case describes the process by which an administrator or master admin views statistical information and data related to the system's usage and performance. This use case enables administrators to gather insights, track key metrics, and analyze trends to make informed decisions and improve the system. | Nguyen Hong Linh | Done | iter3 | none
35 | Function - Grant Admin Rights | Grant Admin Rights | Master Admin | The Grant Admin Rights use case describes the process by which the Master Admin grants administrator rights to a user in the system. This use case enables the Master Admin to delegate administrative privileges to trusted users who can assist in managing the system. | Nguyen Hong Linh | Done | iter3 | none
36 | Function - Add ADS | Add ADS | Business | The "Add Ads" function in social networks is a feature that allows users to create and post advertisements on social networking platforms. | Nguyen Ho Ngoc An | Done | iter3 | none
37 | Function - View ADS | View ADS | Business | The "View Ads Inventory" function allows users to access and browse the available ads inventory. It provides users with a comprehensive overview of the advertisements that are currently active and available for display. | Nguyen Ho Ngoc An | Done | iter3 | none
38 | Function - Update ADS | Update ADS | Business | The "Update Ads" function is a crucial feature in a social network platform that allows advertisers to modify and manage their existing advertisements. This function provides advertisers with the flexibility to make adjustments, improvements, or updates to their ads to ensure they remain relevant and effective in reaching their target audience | Nguyen Ho Ngoc An | Done | iter3 | none
39 | Function - Delete ADS | Delete ADS | Business | The "Delete Ads" function in a social network allows users to remove specific ads from their advertising campaigns. This function provides a convenient way for advertisers to manage their ad content and make adjustments as needed. | Nguyen Ho Ngoc An | Done | iter3 | none
40 | Function - Pay for ADS | Pay for ADS | Business | The "Pay for ADS" function is a paid advertising feature provided by the social network that allows users to promote their content, products, or services to a larger audience by investing money. With this function, users can ensure that their ads are displayed within the news feed of the social network, increasing their visibility and reaching a wider user base. | Nguyen Ho Ngoc An | Done | iter3 | none

## iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Function - Sign up | Sign Up | The Sign Up use case describes the process by which new users create an account on a social networking platform. This use case enables individuals to provide their personal information, such as their name, email address, and password, in order to register and gain access to the platform's features and functionalities. | Nguyen Anh Viet | Done | 3.1.2.1 | II.1
2 | Function - Login | Login | The Login Use use case describes the process of a social networking platform allows users to access their personal accounts using their registered username and password. Users enter their login credentials and then click the "Submit" button to log in to the system. Additionally, this feature provides a "Remember Me" option to save the login information for future access, making it more convenient and time-saving for users to log back into their accounts. | Nguyen Anh Viet | Done | 3.1.2.2 | II.3
3 | Function - Forgot Password | Forgot Password | The Forgot Password feature allows users to recover their forgotten passwords by entering their registered email address and verification code received via email. This feature consists of an email field, an email code field, and a submit button. Users enter their email, receive the code, enter it, and submit to verify and reset their password | Nguyen Anh Viet | Done | 3.1.2.3 | II.3
4 | Function - Logout | Logout | The logout function in a social networking platform allows users to log out of their accounts. When a user selects the logout function, the system will confirm and terminate the user's current login session, redirecting them to either the login page or the main page of the social networking platform. The logout function ensures the security and privacy of users by allowing them to exit their accounts and prevent unauthorised access to their personal information. | Nguyen Anh Viet | Done | 3.1.2.4 | II.3
5 | Function - Edit Profile | Edit Profile | The function of changing user personal information on a platform allows users to modify their account details. It provides users with control over their personal information, enabling them to update and protect their accounts while enhancing security and privacy. | Nguyen Ho Ngoc An | Done | 3.1.2.5 | II.4
6 | Function - Create Post | Create an article | The posting function enables users to create and share content on a social networking platform. Users can compose text, attach media, and choose their audience before publishing the post. It fosters communication, facilitates sharing of thoughts, and encourages engagement with other platform users. | Nguyen Duy Khanh | Done | 3.4.2.1 | II.5
7 | Function - Update Post | Edit a post | The editing feature on social networking platforms allows users to modify and refine their existing posts, ensuring accuracy and relevance. This functionality empowers users to maintain up-to-date information and improve the quality of their shared content. | Nguyen Duy Khanh | Done | 3.4.2.2 | II.5
8 | Function - Delete Post | Delete a post | The ability to delete posts on social networking platforms provides users with the option to remove their previously published content. This feature ensures control over shared information and allows users to manage their online presence effectively. | Nguyen Duy Khanh | Done | 3.4.2.3 | II.5
9 | Function - View Profile | View a user's profile page. | Viewing a personal profile allows users to access and manage their account information, privacy settings, and online identity. It offers control over personal details, enhances security, and enables customization of privacy preferences. | Nguyen Ho Ngoc An | Done | 3.3.2.1 | II.4
10 | Function - View Post | View posts by a user. | The view posts function enables users to browse and engage with a range of shared content. They can like, comment, and share posts to interact and connect with others. It provides a personalized and dynamic experience for staying connected. | Nguyen Ho Ngoc An | Done | 3.3.2.2 | II.4
11 | Function - Share Post | Share a post | The sharing function on social networking platforms enables users to distribute and disseminate interesting content with their network. By sharing posts, users can contribute to discussions, spread awareness, and engage with others. | Nguyen Duy Khanh | Done | 3.4.2.4 | II.5

## iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Function - Find User | Find a user in social network | The "like" functionality allows users to express their appreciation or approval for a specific post. By clicking the "like" button, users can indicate their interest in the content and show their support. This feature enhances user engagement and provides a quick and simple way for individuals to interact with posts they find appealing. | Nguyen Ho Ngoc An | Done | 3.2.2.1 | II.2
2 | Function - Add Friend | Add Friend | Connecting with others on social media is a common and important activity for building relationships and expanding one's online social network. When friending people on social media, users can search, connect, and communicate with others who share similar interests, concerns, or common goals. | Nguyen Anh Viet | Done | 3.6.2.1 | II.10
3 | Function - Accept Friend Request | Accept Friend Request | The "Accept Friend Request" function in a social network allows users to confirm and accept friend requests from others. This is an important part of building an online social network and expanding personal relationships. | Nguyen Anh Viet | Done | 3.6.2.2 | II.10
4 | Function - Unfriend | Unfriend | "Unfriend a friend" is a function in a social networking system that allows a user to unconnect with a friend in his or her friends list. This functionality provides users with the ability to manage and regulate friendships on the platform. | Nguyen Duy Khanh | Done | 3.6.2.3 | II.10
5 | Function - View Friend List | View Friend List | "View Friends List" is a feature in the system that allows users to view a list of their connected friends on the platform. This feature provides a user-friendly interface for users to access and manage their friends' list. | Nguyen Duy Khanh | Done | 3.6.2.4 | II.10
6 | Function - Send Message | Send Message | The Send Message use case describes the process by which a user sends a message to another user within the system. This use case enables users to initiate private conversations, engage in direct communication, and share information with others. | Nguyen Hong Linh | Done | 3.6.2.5 | II.11
7 | Function - View Message | View Message | The View Message use case describes the process by which a user views a received message within the system. This use case enables users to access their message chatBox to read and interact with messages they have received. | Nguyen Hong Linh | Done | 3.6.2.7 | II.11
8 | Function - View Comment | View a comment | The comment feature on social networking platforms allows users to engage in conversations, provide feedback, and share their thoughts on shared posts. By viewing comments, users can actively participate in discussions, gain insights, and build connections within their network. | Nguyen Duy Khanh | Done | 3.5.2.1 | II.6
9 | Function - Create Comment | Create a comment | The commenting function on social networking platforms allows users to engage in conversations, share their thoughts, and provide feedback on shared content. By leveraging the commenting feature, users can actively participate in discussions, express their opinions, and foster connections within the online community. | Nguyen Duy Khanh | Done | 3.5.2.2 | II.6
10 | Function - Update Comment | Edit a Comment | The editing feature on social networking platforms enables users to modify and improve their comments. It allows users to update their thoughts, provide additional context, and make necessary revisions to their shared comments. This functionality promotes active participation, valuable contributions, and enhanced conversation quality within the platform. | Nguyen Duy Khanh | Done | 3.5.2.3 | II.6
11 | Function - Delete Comment | Delete a Comment | The delete comment feature on social networking platforms gives users the power to remove their own posted content. This feature allows users to maintain control over the information they share and effectively manage their online presence. By being able to delete comments, users can ensure the accuracy and relevance of their expressed opinions and protect their privacy by removing personal information if needed. | Nguyen Duy Khanh | Done | 3.5.2.4 | II.6

## iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Function - Add ADS | Add ADS | The "Add Ads" function in social networks is a feature that allows users to create and post advertisements on social networking platforms. | Nguyen Ho Ngoc An | Done | 3.9.2.1 | II.13
2 | Function - View ADS | View ADS | The "View Ads Inventory" function allows users to access and browse the available ads inventory. It provides users with a comprehensive overview of the advertisements that are currently active and available for display. | Nguyen Ho Ngoc An | Done | 3.9.2.2 | II.13
3 | Function - Update ADS | Update ADS | The "Update Ads" function is a crucial feature in a social network platform that allows advertisers to modify and manage their existing advertisements. This function provides advertisers with the flexibility to make adjustments, improvements, or updates to their ads to ensure they remain relevant and effective in reaching their target audience | Nguyen Ho Ngoc An | Done | 3.9.2.3 | II.13
4 | Function - Delete ADS | Delete ADS | The "Delete Ads" function in a social network allows users to remove specific ads from their advertising campaigns. This function provides a convenient way for advertisers to manage their ad content and make adjustments as needed. | Nguyen Ho Ngoc An | Done | 3.9.2.4 | II.13
5 | Function - Pay for ADS | Pay for ADS | The "Pay for ADS" function is a paid advertising feature provided by the social network that allows users to promote their content, products, or services to a larger audience by investing money. With this function, users can ensure that their ads are displayed within the news feed of the social network, increasing their visibility and reaching a wider user base. | Nguyen Ho Ngoc An | Done | 3.9.2.5 | II.13
6 | Function - Report User | Report a User | The Report User use case describes the process by which a user reports another user for inappropriate behavior, harassment, or violation of community guidelines. This use case enables users to flag problematic users, allowing administrators to review and take appropriate action. | Nguyen Hong Linh | Done | 3.8.2.1 | II.7
7 | Function - Report Post | Report a Post | The Report Post use case describes the process by which a user reports a post that violates the platform's guidelines or contains inappropriate content. This use case enables users to flag posts that they find offensive, harmful, or in violation of community standards, allowing administrators to review and take appropriate action. | Nguyen Hong Linh | Done | 3.8.2.2 | II.9
8 | Function - Report Comment | Report a Comment | The Report Comment use case describes the process by which a user reports a comment that violates the platform's guidelines or contains inappropriate content. This use case enables users to flag comments that they find offensive, harmful, or in violation of community standards, allowing administrators to review and take appropriate action. | Nguyen Hong Linh | Done | 3.8.2.3 | II.8
9 | Function - View Post Report | View Post Report | The View Post Report use case describes the process by which an administrator views a list post report within the system. | Nguyen Hong Linh | Done | 3.8.2.4 | II.9
10 | Function - Delete Post Report | Delete Post Report | The Delete Port Report use case describes the process by which an administrator deletes a port report from the system. This use case enables administrators to permanently remove port reports for various reasons, such as outdated information, duplicate entries, or data privacy considerations. | Nguyen Duy Khanh, Nguyen Hong Linh | Done | 3.8.2.5 | II.9
11 | Function - View Comment Report | View Comment Report | The View Comment Report use case describes the process by which an administrator views a list comment report within the system. | Nguyen Hong Linh | Done | 3.8.2.6 | II.8
12 | Function - Delete Comment Report | Delete Comment Report | The Delete Comment Report use case describes the process by which an administrator deletes a comment report from the system. This use case enables administrators to permanently remove comment reports for various reasons, such as inappropriate content, spam, or policy violations. The deletion of comment reports helps maintain the integrity and quality of user-generated content within the system. | Nguyen Duy Khanh, Nguyen Hong Linh | Done | 3.8.2.7 | II.8
13 | Function - View User Report | View User Report | The View User Report use case describes the process by which an administrator views a list user's account report within the system. | Nguyen Hong Linh | Done | 3.8.2.8 | II.7
14 | Function - Lock User Account | Lock User Account | The Lock User Account use case describes the process by which an administrator locks a user's account within the system. This use case enables administrators to restrict user access and prevent further use of the account due to violations, suspicious activities, or other administrative reasons. | Nguyen Hong Linh | Done | 3.8.2.9 | II.7
15 | Function - Delete User Account | Delete User Account | The Delete User Account use case describes the process by which an administrator deletes a user's account from the system. This use case enables administrators to permanently remove user accounts due to various reasons, such as policy violations or user request. | Nguyen Hong Linh | Done | 3.8.2.10 | II.7
16 | Function - View Statistics | View Statistics | The View Statistics use case describes the process by which an administrator or master admin views statistical information and data related to the system's usage and performance. This use case enables administrators to gather insights, track key metrics, and analyze trends to make informed decisions and improve the system. | Nguyen Hong Linh | Done | 3.8.2.11 | II.14
17 | Function - Grant Admin Rights | Grant Admin Rights | The Grant Admin Rights use case describes the process by which the Master Admin grants administrator rights to a user in the system. This use case enables the Master Admin to delegate administrative privileges to trusted users who can assist in managing the system. | Nguyen Hong Linh | Done | 3.8.2.12 | II.15
18 | Function - Create Brand | Create Brand | The brand-building function in social media is a feature that helps users build and manage their brand on the social media platform. It provides users with tools and resources to create and shape brand elements such as logo, intro, email, phone, address. The brand-building function also offers tools for users to create advertisements based on their brand. | Nguyen Anh Viet | Done | 3.7.2.1 | II.10